## Sheet1
Task | Assignee | Deadline | Notes
Configuration Management Plan | Developers | 2016-04-10 | Specify the details of project directory and the strategies to adopt when changes occur.
Revise the Project Plan | PM | 2016-04-10 | https://www.assembla.com/spaces/cis422_template/wiki/Project_Plan
Software Requirements Specification | SE&Achitect | 2016-04-10 | Recommend to use DFD which is simple and explicit
Record WeekData | ALL | 2016-04-10 | All members should have the consciousness of recording wordload form the first week.
First all-sites meeting | ALL | 2016-04-10 | Every one should prepare a self-introduction written in English(about one minute), and the meeting will start at 9 am, April 10th. The location is undetermined.
Note: Developer Logs（"https://www.assembla.com/spaces/cis422_template/wiki/Developer_Logs_(or_Blogs)"）