## Sheet1
Task | Assignee | Deadline | Notes
Revise SRS | SE&Achitect | 2016-04-15
Translate SRS | Liaison | 2016-04-17
Finish draft of AS(Architecture & Interface Speicification) | Achitect | 2016-04-15
Translate AS | Liaison | 2016-04-17
Configure the development environment and create working directory | Developer | 2016-04-17
Contact with UO | PM&Liaison | 2016-04-17
Record WeekData | ALL | 2016-04-17 | All members should have the consciousness of recording wordload form the first week.