## Sheet1
Task | Assignee | Deadline | Notes
Finish AS(Architecture & Interface Speicification) | Shuai Shao, Feng Wang | 2016-04-21 | The code can start to be written when writing Interface spec.
Rivise SRS | Limeng Qiao | 2016-04-23 | The DFD needs to be modified, for example, change Username to Email
Translate AS | Qianwei Wang | 2016-04-23 | It's better to finish AS in Saturday so that we can let UO review it when having meeting with them.
Configure the development environment and create working directory | Feng Wang | 2016-04-20 | Finish it as soon as possible.
Write Test Case | Rongzhi Zhang, Qianshan Yu | 2016-04-23
Contact with UO | Qianwei Wang, Qianshan Yu | 2016-04-22 | We will have meeting with UO Database group on Saturday.
Record WeekData | ALL | 2016-04-24 | All members should have the consciousness of recording wordload form the first week.
Note: The purpose of communication with UO is to unify the interface so that we can connect to each other. And we should also review the documents each other.
Note: UNC has posted their documents to Assembla and we can even copy them. (I've uploaded them to QQ-Group: UNC-Deliverables.rar)